## Sheet1
Item | P | I | Risk (P*I) | Recognized | Mitigated/ Resolved | ROAM | How
I'm unable to implement physics for my walls | 20 | 40 | 800 | 2024-03-18 | Mitigated | M | I will spend the next week working on this
I am unable to implement funcitonality for the holes | 5 | 40 | 200 | 2024-03-19 | Mitigated | M | I will spend the next week working on this. This is a task I already have ideas for how to acomplish and I know it is within my wheelhouse.
I am unable to implement more accurate physics | 5 | 40 | 200 | 2024-03-20 | Mitigated | M | This is not the end of the world, my game will still be playable
I break my code and am unable to fix it | 2 | 70 | 140 | 2024-03-16 | Mitigated | M | I am continuously saving backup copies of my code in case of this
I am not able to get the menu to work | 8 | 13 | 104 | 2024-04-19 | Accepted | A | If it happens it happens. It is not the end of the world.
I break my laptop and my project is lost | 1 | 100 | 100 | 2024-03-21 | Owned/Resolved | O/R | I will backup my code to github after each update
I am not successful in testing game ending conditions | 2 | 40 | 80 | 2024-03-21 | Mitigated | M | Test and get TA/Instructor help if not working
I break my board | 3 | 13 | 39 | 2024-03-21 | Accepted | A | If it happens I will react. Buy different board/use others for testing
I am unable to implement PWM for the LEDs | 2 | 13 | 26 | 2024-03-21 | Mitigated | M | Test and get TA/Instructor help if not working. Not the end of the world

## Sheet2
Valid Modified Fibonacci values
1
2
3
5
8
13
20
40
70
100